## 1. Workflow & Roles
TRACKADEMY — THE WORK (current production process)
How a sub-topic moves from idea to published video. Pre-filled with the system's current logic as of 12-Jun-2026. Review and amend.
ROLES
Program Head | Admin & sole owner of the portal. Assigns everyone, can delete, full visibility. (Sai Chitra)
Manager | Oversees assigned programs; can assign within scope.
Team Lead | Assigns work to their team (trainers); sees only their programs.
Trainer | Records the content — owns PPT → Script → Presentation → Shooting.
Editor | Edits the recorded video. Sees ONLY videos assigned to them.
Reviewer | Rates the recording (Shoot Review) and approves the final cut (Final Review).
Mentor | Preps a topic through gated steps to become deploy-ready (separate track).
THE 7-STAGE PIPELINE
Step | Stage | Who does it | Starts when (entry) | Done when (gate/exit) | Status options | Notes
1 | PPT | Trainer | Program/topic assigned to the trainer | PPT marked Completed | Not Started · In Progress · Blocked · Reshoot · Completed | First deliverable.
2 | Script | Trainer | PPT completed | Script marked Completed | same
3 | Presentation | Trainer | Script completed | Presentation marked Completed | same | Slides ready to record.
4 | Shooting | Trainer | Studio slot booked · Presentation done | Shooting marked Completed | same | Recording happens in studio.
5 | Shoot Review | Reviewer / Program Head | Shooting Completed | Shoot Review Completed (quality rated) | Not Started · In Progress · Completed | Rates raw recording quality.
6 | Editing | Editor (assigned) | Shoot Review Completed | Final output = Completed | Pending · In Progress · Reshoot · Completed | Editor's single status = Final output.
7 | Final Review | Reviewer / Program Head | Editing (Final output) Completed | Final Review Completed = Published | Not Started · In Progress · Completed | Approves the final cut.
Reshoot is a status, not a stage: when set on Editing it bounces the video back to the trainer's Shooting to re-record (see Sheet 2).

## 2. Assignment Rules
ASSIGNMENT & RE-ASSIGNMENT RULES — define & amend
Yellow cells are for the Program Head to fill in. 'Program Head decision' = Keep / Amend. Rows D1–D5 are policies the system does NOT yet enforce — define them so the dev team can build them.
A. ASSIGNMENT (who gets the work)
Rule ID | Area | Trigger / Condition | Current behaviour in the system | When should it be (re)assigned? | Goes to whom? | What happens on (re)assignment | Program Head decision | Amended rule / notes
A1 | Content | New program / topic needs an owner | Program Head assigns a trainer at program, subject, chapter, topic or sub-topic level; lower levels inherit the owner (effective owner). |  | Trainer | Trainer sees it in My Work / My Day. | Keep
A2 | Editor | Video has passed Shoot Review and needs editing | Program Head multi-selects videos in the Editing queue and bulk-assigns an editor. Only videos past Shoot Review can be assigned. |  | Editor | Editor sees ONLY their assigned videos in their My Work queue. | Keep
A3 | Visibility | Who can see which content | 'Sees all content' toggle gives full visibility; otherwise a person sees only their assigned/scoped programs. Team Leads see only their programs. |  | n/a | Controls list scope, not ownership. | Keep
A4 | Permission | Who is allowed to assign | Only Program Head (admin), or a person with 'Can assign', or a Team Lead, may assign work. |  | n/a | Assign controls are hidden for everyone else. | Keep
B. RE-ASSIGNMENT & RESHOOT (when work moves)
Rule ID | Area | Trigger / Condition | Current behaviour in the system | When should it be (re)assigned? | Goes to whom? | What happens on (re)assignment | Program Head decision | Amended rule / notes
R1 | Reshoot | Editor sets Final output = Reshoot | System sends the video back to the SAME assigned trainer; Shooting status returns to In Progress. | Immediately on Reshoot | Assigned trainer | Trainer re-records; once Shooting is Completed again the normal flow continues (Shoot Review → Editing). | Keep
R2 | Reshoot | Reshoot is needed but the trainer is inactive / removed | Falls back to the open queue (unassigned). | When original trainer is inactive | Open queue → Program Head | Program Head reassigns to another trainer to re-record. | Keep
R3 | Flow | Editing Final output = Completed | Video advances into the Final Review (reviewer) queue. | Automatic on Completed | Reviewer / Program Head | Reviewer approves → Published. (If no reviewer assigned, Program Head reviews.) | Keep
R4 | Flow | Shooting marked Completed | Video advances into the Shoot Review queue. | Automatic on Completed | Reviewer / Program Head | Reviewer rates quality; pass → Editing queue. | Keep
C. POLICIES TO DEFINE (not yet enforced — Program Head to specify)
Rule ID | Area | Trigger / Condition | Current behaviour in the system | When should it be (re)assigned? | Goes to whom? | What happens on (re)assignment | Program Head decision | Amended rule / notes
D1 | Editor load | An editor has too many videos | No limit today — assignment is manual.
D2 | SLA / delay | A stage breaches its due date | Flagged in SLA & Delays, but no auto-reassign.
D3 | Leave vs exit | Trainer on leave (temporary) vs removed (permanent) | Only 'inactive' is handled (R2). No temporary-hold rule.
D4 | Reshoot limit | Same video reshot many times | Unlimited reshoots today.
D5 | Review reject | Final Review is NOT approved | Not defined — reviewer just leaves it incomplete.